## Sheet1
Task | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. UV performance of existing Skippers | bar: Year 1 Q1 to Year 3 Q2
2. Complex UV Bandpass Skippers | bar: Year 2 Q1 to Year 3 Q4
3. UV Block Filters Skippers | bar: Year 3 Q3 to Year 5 Q4
4. Characterization
4a. Performance of Existing Skippers | bar: Year 1 Q1 to Year 3 Q4
5. Lot Runs
5a. Update Design, Lot Run 1 | bar: Year 1 Q1 to Year 3 Q3
5b. Testing Lot 1, Delta-doping Lot 1 | bar: Year 2 Q3 to Year 4 Q4
5c. Lot Run 2 (Other Funds) | bar: Year 3 Q4 to Year 5 Q4
6. On-sky Testing | bar: Year 4 Q3 to Year 5 Q4